## Instructions
Risk Assessment
www.edmundotorquemada.com
General
| a. | This file is fully editable, customize it to your liking. Be sure not to delete items marked as "Do not delete"
| b. | To rename a tab, right-click on it, click on "Rename" and enter your preferred name
| c. | To delete a tab, right-click on it, click on "Delete"
| d. | To hide a tab, right-click on it, click on "Hide"
| e. | To unhide tabs, right-click on any visible tab, click "Unhide", select the tab to unhide
| f. | To "freeze" or "unfreeze" header go to "View", click on "Freeze Panes", then click on "Freeze Panes" or "Unfreeze Panes"
Instructions
| 1 | Risk | Enter summary of the risk
| 2 | Description | Describe the exact nature of the risk, impact, and driver (if known)
| 3 | Probability | Select: Low, Medium, or High using the drop-down
| 4 | Impact | Select: Low, Medium, or High using the drop-down
| 5 | Mitigation | Describe how you can mitigate this risk (reduce probability)
| 6 | Contingency | Describe what you can do if the risk happens
| 7 | Owner | Enter the name of the owner to manage this risk
| 8 | Status | Select: In progress (risk is being worked on), On hold (no action is taken on the risk), or Closed (risk is no longer a concern)
| 9 | Comments | Add any noteworthy information
| 10 | To edit drop-downs unhide the tab "Do not delete" and edit labels

## Risk Assessment
Risk Assessment
www.edmundotorquemada.com
Item | Risk | Description | Probability | Impact | Mitigation | Contingency | Owner | Status | Comments
1 | Budget may be exceeded | Total costs for project may exceed the allocated $22,000 budget, driven by transportation costs. | High | Medium | Do value-analysis to reduce costs in other categories, bid transportation services. | Reduce scope of project; request short-term loan | Cindy M. | In progress | Awaiting results of bids. If unable to reduce transp. costs we will reduce scope of project.
2 | Website development delay | Developer is taking longer than anticipated | Medium | High | Meet with developer to understand driver for delay; simplify website requirements; secure additional help for developer. | Hire pre-made services while website is finished (shopify; godaddy; wix; etc.) | John D. | Closed | We set-up Shopify for six months while developer completes website
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Do not delete (hidden)
Risk Assessment
www.edmundotorquemada.com
This tab contains the lists of the table drop-downs
Probability | Impact | Status
Low | Low | In progress
Medium | Medium | On hold
High | High | Closed